|  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| No. | Objective | Strategy | Activity | Responsible person | Time line | Budget | Process Indicator |
| 01. | To stream line the QM activities in the health institutions in Gampaha district  | Preparing action plans for each health institutions for 2019(both hospitals & MOH offices) | Workshop on preparing action plans for,1.For focal points at hospitals2.For designated officer at MOHs | Mo-QM(focal point) at RDHS | August | HSDP | % of hospitals & MOH offices prepared action plans before 2019 January |
| 02. | To monitor the QM activities in health institutions | 1.Review activities at district level2.Supervisory visit to the institutions | Review meetings at RDHS officeI. Visit the hospitals by a team consist of focal point at RDHS and one independent Mo(QM) from a hospitalii.Visit the MOH offices | Mo-QM(focal pointMo-QM(focal point | April & SeptemberTwo hospital for a month Do supervision incorporated into the MOH supervision  | HSDP | % of hospitals & MOH offices participated% of hospitals & MOH offices supervised |
| 03. | To improve customer satisfaction and quality of care given to patients at health institutions at the district  | Capacity building | Workshops at institutional level1.DGH Negambo & Gampaha2.B.H wathupitiwala & meerigama3.Divisional hospital Divulapitiya, Kiribathgoda, Dompe, Minuwangoda | Mo-focal point at RDHS & relevant focal point at the institutions  | From June to September | HSDP | % of institutions completed work shop |